**TADCASTER NEIGHBOURHOOD PLAN PROJECT PLAN**

**24TH AUGUST 2021**

**COMMUNITY ENGAGEMENT & INVOLVEMENT**

* **Policy Intentions Document (PID) consultation (4 weeks) – Oct/Nov 2021**
* Formal Regulation 14 consultation (6 weeks) – Apr/May 2022

**WRITING THE PLAN**

* **Finalise PID for consultation – Sept/Oct 2021**
* Analyse PID consultation results –Nov/Dec 2021
* Draft Pre-Submission NDP incl. evidence review (3 months) – Dec 2021/Mar 2022
* Seek EU screening opinion from LPA – Mar 2022
* Finalise plan for Regulation 14 consultation – Mar/Apr 2022
* Analyse Regulation 14 consultation results (2 months) – June/July 2022
* Amend plan/check evidence following Regulation 14 consultation (1 month) – Aug 2022
* Finalise NDP for submission – Sept 2022
* Sustainability assessment of plan – Sept 2022
* Prepare Consultation Statement – Sept 2022
* Prepare Basic Conditions Statement – Sept 2022
* Initiate examiner appointment process with LPA – Oct 2022
* Submit NDP to LPA – Oct 2022